## Week 4
Person | Question | Week 4: 14/9/2019 to 15/9/2019
|  | Saturday | Sunday
Jaslyn Toh | What did you do yesterday? | NIL | Planned for 16/9 meeting
| What will you do today? | Continue planning for 16/9 meeting | Make schedule changes and updates
| Do you have any obstacles? | NIL | NIL
Lai See Hoe | What did you do yesterday? | NIL | Read up on class and classDAOs and functionalities
| What will you work on today? | Read up on class and classDAOs, and functionalities | Re-look bootstrap in Pokemon example
| Do you have any obstacles? | NIL | NIL
Leonard Wong | What did you do yesterday? | NIL | Re-look at functionalities
| What will you work on today? | Re-look at functionalities | Start planning the code for Bid bootstrap (class, reading & processing of csv)
| Do you have any obstacles? | NIL | NIL
Serene | What did you do yesterday? | NIL | Read up on functionalities, classes
| What will you work on today? | Read up on functionalities, classes | Revise on classesDAO
| Do you have any obstacles? | NIL | NIL
Yi Bing | What did you do yesterday? | NIL | Read up on functionalities, classes
| What will you work on today? | Read up on functionalities, classes | Plan codes for course and prerequisite class and classDAOS
| Do you have any obstacles? | NIL | NIL

## Week 5
Person | Question | Week: 16/9/2019 to 23/9/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Jaslyn Toh | What did you do yesterday? | Planned for today's meeting | Relook at functionalities | Coach using the prerequisite csv. | Transfer the schedule into the google sheets | Check for bugs in codes
| What will you do today? | Relook at functionalities | Coaching using the prerequisite csv. | Transfer the schedule into the google sheets | Check for bugs in codes | Prepare test plans for the meeting
| Do you have any obstacles? | NIL | NIL | Transferring the schedule is tedious as the formats will be shuffled | NIL | NIL
Lai See Hoe | What did you do yesterday? | Re-look bootstrap in Pokemon example | Plan the functionalities of the DAO and boot strap in section | Create database, Pre requsite class, Prereq class dao and boot strap | To push Course, courseDAO, section and sectionDAO | Check for bugs in codes
| What will you work on today? | Plan the functionalities of the DAO and boot strap in section | Create database, Pre requsite class, Prereq class dao and boot strap | To push Course, courseDAO, section and sectionDAO | Check for bugs in codes | Prepare test cases for the meeting
| Do you have any obstacles? | NIL | NIL | Faced slight issues when creating the Prerequisite bootstrap | NIL | NIL
Leonard Wong | What did you do yesterday? | Start planning the code for Bid bootstrap (class, reading & processing of csv) | Start on Bid DAO and Bid.php structure | Continue with bid DAO and Bid.php | Pushed course_completed, course_completedDAO, student, studentDAO, bidDAO and Bid.php | Check for bugs in codes
| What will you work on today? | Start on Bid DAO and Bid.php structure | Continue with bid DAO and Bid.php | Finishing student, studentDAO, bidDAO and Bid.php | Check for bugs in codes | Prepare test cases for the meeting
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL
Serene | What did you do yesterday? | Revise on classesDAO | Read up on pokemon example | Start on student.php and studentDAO.php structure | Aid leonard in pushing codes | Check for bugs in codes
| What will you work on today? | Read up on Pokemon example | Start on student.php and studentDAO.php structure | Aid leonard in pushing bid, bidDAO, student and studentDAO | Check for bugs in codes | Prepare test cases for the meeting
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL
Yi Bing | What did you do yesterday? | Plan codes for course and prerequisite class and classDAOS | Read up on Pokemon example | Create database, Pre requsite class, Prereq class dao and boot strap | Aid See Hoe in pushing course, courseDAO, section and sectionDAO | Check for bugs in codes
| What will you work on today? | Read up on Pokemon example | Create database, Pre requsite class, Prereq class dao and boot strap | Aid See Hoe in pushing course, courseDAO, section and sectionDAO | Check for bugs in codes | Prepare test cases for the meeting
| Do you have any obstacles? | NIL | NIL | Faced some issues with PrereqDAO | NIL | NIL

## Week 6
Person | Question | Week: <starting date> to <ending date>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Jaslyn Toh | What did you do yesterday?
What will you do today?
Do you have any obstacles?
Lai See Hoe | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Leonard Wong | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Serene | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Yi Bing | What did you do yesterday?
What will you work on today?
Do you have any obstacles?