## Schedule
Iteration No. | Task No. | Description | Planned Start Date / Time | Planned End Date / Time | Hours Planned | Actual Start Date / Time | Actual End Date / Time | Actual Hours Spent | Location | Status | Done By (Use Initials. Leader in bold)
1 | 1 | (Meeting 1) Read updated project wiki | 2019-09-14 10:00 | 2019-09-14 11:45 | 1.75 | 2019-09-14 10:00 | 2019-09-14 11:45 | 1.75 | SIS Level 3 | Completed | JT, SH, LW, YB, SA
1 | 2 | (Meeting 1) Finalise all Iterations dates | [7 empty] | Completed | JT, SH, LW, YB, SA
1 | 3 | (Meeting 1) Allocate Programming Pairs and Rotation | [7 empty] | Completed | JT, SH, LW, YB, SA
1 | 4 | (Meeting 1) Allocate PM for each Iteration | [7 empty] | Completed | JT, SH, LW, YB, SA
1 | 5 | (Meeting 1) Plan out Task List for Iteration 1 | [7 empty] | Completed | JT, SH, LW, YB, SA
1 | 6 | (Meeting 2) Finalise Work Schedule for Iteration 1 | 2019-09-16 17:00 | 2019-09-16 18:00 | 1 |  |  | 1 | SIS Level 3 |  | JT, SH, LW, YB, SA
1 | 7 | (Meeting 2) Go through Functionalites in detail | 2019-09-16 18:00 | 2019-09-16 19:00 | 1 |  |  |  | SIS Level 3 |  | JT, SH, LW, YB, SA
1 | 8 | (Meeting 2) Splitting the work | 2019-09-16 19:00 | 2019-09-16 19:15 | 0.25 |  |  |  | SIS Level 3 |  | JT, SH, LW, YB, SA
1 | 9 | Pair Programming session 1: YB&SH Create Database, Prerequisite class, Prerequisite classDAO and Bootstrap *(To commit & push by 8pm) | 2019-09-17 18:00 | 2019-09-17 20:00 | 2 |  |  |  | SIS Level 3 |  | YB, SH
1 | 10 | Pair Programming session 2: SH&YB Create course.php, courseDAO.php, section.php and sectionDAO.php *(To commit & push by 2pm) | 2019-09-18 12:00 | 2019-09-18 14:00 | 2 |  |  |  | SIS Level 3 |  | YB, SH
1 | 11 | Pair Programming session 3: LW&SA Create student.php, studentDAO.php, bid.php and bidDAO.php *(To commit & push by 9pm) | 2019-09-18 19:00 | 2019-09-18 21:00 | 2 |  |  |  | SIS Level 3 |  | LW, SA
1 | 12 | Pair Programming session 4: SA&LW Create course_completed.php, course_completedDAO.php | 2019-09-19 19:00 | 2019-09-19 21:00 | 2 |  |  |  | SIS Level 3 |  | LW, SA
1 | 13 | (Meeting 3) Group Progress update, discuss Test case and Test plans | 2019-09-20 19:00 | 2019-09-20 20:00 | 1 |  |  |  | SIS Level 3 |  | JT, SH, LW, YB, SA
1 | 14 | Pair Programming session 5: SH&YB Bootstraps creation for Prerequisite, Course, Section *(To commit & push by 6pm) | 2019-09-21 16:00 | 2019-09-21 18:00 | 2 |  |  |  | SIS Level 3 |  | YB, SH
1 | 15 | Pair Programming session 6: LW&SA Bootstraps creation for Student, Course_completed, Bid *(To commit & push after 6pm but by 9pm) | 2019-09-21 19:00 | 2019-09-21 21:00 | 2 |  |  |  | SIS Level 3 |  | LW, SA
1 | 16 | (Meeting 4 Online) Both Pairs to Come up with Test cases for Validations, with a list on what they conditions they have to test, upload on excel sheet in Testing | 2019-09-22 13:00 | 2019-09-22 16:00 | 3 |  |  |  | Skype |  | JT, SH, LW, YB, SA
1 | 17 | Pair Programming session 7: LW & SA Add-On code to ensure Validations are correct for all their Bootstraps *(To commit & push after 6pm but by 9pm) | 2019-09-24 16:00 | 2019-09-24 18:00 | 2 |  |  |  | SIS Level 3 |  | LW, SA
1 | 18 | Pair Programming session 8: SH & YB Add-On code to ensure Validations are correct for all their Bootstraps *(To commit & push after 6pm but by 9pm) | 2019-09-24 19:00 | 2019-09-24 21:00 | 2 |  |  |  | SIS Level 3 |  | YB, SH
1 | 19 | Pair Programming session 9: SH & YB Work on Login Page and authentication *(To commit & push by 9pm) | 2019-09-25 19:00 | 2019-09-25 21:00 | 2
1 | 20 | (Meeting 5) Testing out the codes together | 2019-09-26 18:45 | 2019-09-26 20:00 | 1.25
1 | 21 | BUFFER | 2019-09-27 | 2019-09-27
1 | 22 | END OF ITERATION 1 | 2019-09-28 | 2019-09-28
2 | 23 | Start of Iteration 2 | 2019-09-28 | 2019-09-28
2 | 24 | Finale Schedule Plan
2 | 25
26
27