## Instructions
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Our Bug Metrics
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 1 | retrieve($course) in course DAO | Not all data was called in the select statement which made it impossible to create course objects. Results were also not appended in an array. | High | 5
2 | 1 | retrieve($course) in Prerequisite DAO | Not all data was called in the select statement which made it impossible to create prereq object. Results were also not appended in an array. | High | 5
3 | 1
4 | 1
5 | 1
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198

## Our Bug Log
Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team)
1 | 1 | retrieve($course) in course DAO
2 | 1
3 | 1
4 | 1
5 | 1
6 | 1
7 | 1
8 | 1
9
9
10
11
13
14
15
16
17
18
19
20
21

## Bug Metrics SAMPLE
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 2 | Login (User) | Failed login with correct username and correct password | High | 5 | 27 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
2 | 2 | Login (User) | Failed login with correct username and wrong password | High | 5
3 | 2 | Login (User) | Failed login with wrong username and correct password | High | 5
4 | 2 | Login (Admin) | After successful login, login did not store name in session for display use at index_admin | Low | 1
5 | 2 | Login (User) | After successful login, login did not store name in session for display use at index | Low | 1
6 | 2 | Bootstrap | Crashes on upload with a "duplicate entry" database error | Critical | 10
7 | 3 | Bootstrap | Failed to print correct error message for invalid username | Low | 1 | 20 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
8 | 3 | Bootstrap | Failed to validate the "timestamp" in location.csv | Low | 1
9 | 3 | Bootstrap | Printed wrong error messages | Low | 1
10 | 3 | HeatMap | Unable to retrieve Arraylist sucessfully | High | 5
11 | 3 | HeatMap | Fail to load timepicker function | Low | 1
12 | 3 | HeatMap | Cannot load date and time picker function after importing navbar.jsp | Low | 1
13 | 3 | HeatMap | Did not retrieve the last location update | Critical | 10
14 | 4 | Popular Place | Could not print K number of places | High | 5 | 20 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
15 | 4 | Popular Place | Null pointer exception raised when dealing with no data | High | 5
16 | 4 | Popular Place | Could not select "K" | High | 5
17 | 4 | Bootstrap | Could not delete from table when bootstrapping | High | 5
18 | 4 | Breakdown of Y&G | Retreive output table is not aligned properly | Low | 1 | 12 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
19 | 4 | Breakdown of Y&G | Null pointer exception raised when retreiving error message | High | 5
20 | 4 | Breakdown of Y&G | Unable to calculate percentage | Low | 1
21 | 4 | Breakdown of Y&G | Issue when retrieving total number of users, and cause null pointer exceptions | High | 5
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198

## Bug Log Sample
Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team)
1 | 1 | retrieve($course) in course DAO | Not all data was called in the select statement which made it impossible to create course objects. Results were also not appended in an array. | Resolved | 2017-10-01 | 2017-10-01 | J & K
2 | 1 | retrieve($course) in Prerequisite DAO | Not all data was called in the select statement which made it impossible to create prereq object. Results were also not appended in an array. | Resolved | 2017-10-01 | 2017-10-01 | J & K
3 | 1 | 0 | 0 | Resolved | 2017-10-01 | 2017-10-01 | J & K
4 | 1 | 0 | 0 | Unresolved | 2017-10-01
5 | 1 | 0 | 0 | Resolved | 2017-10-01 | 2017-10-01 | J & K
6 | 0 | 0 | 0 | Resolved | 2017-10-01 | 2017-10-04 | H & W
7 | 0 | 0 | 0 | Resolved | 2017-10-04 | 2017-10-05 | H & W
8 | 0 | 0 | 0 | Resolved | 2017-10-05 | 13/10/2017 | H & W
9 | 4 | Bootstrap | 0 | Resolved | 22/10/2017 | 22/10/2017 | H & W
9 | 3 | Heatmap | 0 | Resolved | 13/10/2017 | 13/10/2017 | W & P
10 | 3 | Heatmap | 0 | Resolved | 13/10/2017 | 13/10/2017 | W & P
11 | 3 | Heatmap | 0 | Resolved | 13/10/2017 | 13/10/2017 | W & P
13 | 3 | Heatmap | 0 | Resolved | 14/10/2017 | 14/10/2017 | H & J
14 | 4 | Popular Place | 0 | Resolved | 22/10/2017 | 22/10/2017 | H & J
15 | 4 | Popular Place | 0 | Resolved | 22/10/2017 | 22/10/2017 | H & K
16 | 4 | Popular Place | 0 | Resolved | 22/10/2017 | 22/10/2017 | H & K
17 | 0 | 0 | 0 | Unresolved | 22/10/2017
18 | 0 | 0 | 0 | Unresolved | 22/10/2017
19 | 0 | 0 | 0 | Resolved | 2017-10-21 | 2017-10-21 | J & P
20 | 0 | 0 | 0 | Resolved | 2017-10-21 | 2017-10-21 | J & P
21 | 0 | 0 | 0 | Resolved | 2017-10-21 | 2017-10-21 | J & P