## Instructions
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Our Bug Metrics
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 1 | Bootstrap | Not all data was called in the select statement which made it impossible to create course objects. Results were also not appended in an array. retrieve($course) in course DAO | High | 5 | 5 | Stopped Current Development and inform the PM. Scheduled another session for debugging.
2 | 1 | Bootstrap | Not all data was called in the select statement which made it impossible to create prereq object. Results were also not appended in an array. retrieve($course) in Prerequisite DAO | High | 5 | 5 | Stopped Current Development and inform the PM. Scheduled another session for debugging.
3 | 1 | Bootstrap | Spelling error in function name. retrieve($course) in Prerequisite DAO | Low | 1 | 1 | Debugged once the bug is spotted
4 | 1 | Bootstrap | Did not Initialise $course_processed | Low | 1 | 1 | Debugged once the bug is spotted
5 | 1 | Bootstrap | Returned an array of objects instead of 1 object. retrieve($userid) in StudentDAO | Low | 1 | 1 | Debugged once the bug is spotted
6 | 1 | Bootstrap | When appending object in retrieve($course), wrong class (course) was used. retrieve($course) in Prerequisite DAO | High | 5 | 5 | Stopped Current Development and inform the PM. Scheduled another session for debugging.
7 | 1 | Bootstrap | SQL statement only retrieves userid and amount. retrieve($userid) in BidDAO | High | 5 | 5 | Stopped Current Development and inform the PM. Scheduled another session for debugging.
8 | 1 | Bootstrap | Remove function in BidDAP only pass in userid instead of both userid and code | High | 5 | 5 | Stopped Current Development and inform the PM. Scheduled another session for debugging.
9 | 1 | Bootstrap | Empty function treats 0 as empty. Changed to comparison with "" in Common.php | Low | 1 | 1 | Debugged once the bug is spotted
10 | 1 | Bootstrap | Updated isEmpty($var) to check if the data is "" and not empty() | Low | 1 | 1 | Debugged once the bug is spotted
11 | 1 | Bootstrap | Changed sql statement for retrieveAll(), Changed retrieve(userID) function to return an array, Debugged Remove($userid) function | High | 5 | 5 | Stopped Current Development and inform the PM. Scheduled another session for debugging.
12 | 1 | Bootstrap | Wrong SQL statement changed to * | High | 5 | 5 | Stopped Current Development and inform the PM. Scheduled another session for debugging.
13 | 1 | Bootstrap | Code Sequence wrong, empty() takes 0 as empty, thus changed to string comparison * | Low | 1 | 1 | Debugged once the bug is spotted
14 | 2 | Add Bid | Variable names in course class differs from bidhome.php | Low | 1 | 1 | Debugged once the bug is spotted
15 | 2 | validate no class time clashed | loops for validating no class time clashed and loops for validating no exam time clashed should not be nested | High | 5 | 5 | Stopped Current Development and inform the PM. Scheduled another session for debugging.
16 | 2 | assign the value to username | hard code username | Low | 1 | 1 | Debugged once the bug is spotted
17 | 2 | assign the value to round | hard code round | Low | 1 | 1 | Debugged once the bug is spotted
18 | 2 | Round 2 Clearing | Changed variable name | Low | 1 | 1 | Debugged once the bug is spotted
19 | 2 | Round 2 Clearing | added min_bid row | Low | 1 | 1 | Debugged once the bug is spotted
20 | 2 | Round 2 Clearing | admin_homepage.php doesn’t lead to correct pages when the various buttons are pressed | High | 5 | 5 | Stopped Current Development and inform the PM. Scheduled another session for debugging.
21 | 2 | Round 2 Clearing | bootstrap_process.php had a missing ?> in the php file | Low | 1 | 1 | Debugged once the bug is spotted
22 | 2 | Add Bid | Edollar is not updated on bidding.php after submit button. Only edollar left is updated. | High | 5 | 5 | Stopped Current Development and inform the PM. Scheduled another session for debugging.
23 | 2 | Add Bid | bidding.php shows error as did not code what to display if there are no sections available. | Low | 1 | 1 | Debugged once the bug is spotted
24 | 2 | Round 2 Clearing | bid table not cleared during clearing | High | 5 | 5 | Stopped Current Development and inform the PM. Scheduled another session for debugging.
25 | 2 | meet Criteria | fail to test the completed course in "course_comp.php" | Low | 1 | 1 | Debugged once the bug is spotted
26 | 2 | Bidding | Bidding page cannot access because path called is wrong | Low | 1 | 1 | Debugged once the bug is spotted
27 | 2 | Admin Clearing | Failed bids are not added to Fail bid table | High | 5 | 5 | Debugged once the bug is spotted
28 | 3 | JSON Start | Start round message prints 0 when round is 2 | Low | 1 | 1 | Debugged once the bug is spotted
29 | 3 | JSON Stop | Did not update student's bid | Low | 1 | 1 | Debugged once the bug is spotted
30 | 3 | JSON Start | Did not properly print out message with [] | Low | 1 | 1 | Debugged once the bug is spotted
31 | 3 | Round 1 Clearing | added student object instead of bid object into fail_bid table | Low | 1 | 1 | Debugged once the bug is spotted
32 | 3 | bidding status | spelling error | Low | 1 | 1 | Debugged once the bug is spotted
33 | 3 | bidding status | return wrong message as round is hardcoded | Low | 1 | 1 | Debugged once the bug is spotted
34 | 3 | Stop round | updates the round table with wrong status | Low | 1 | 1 | Debugged once the bug is spotted
35 | 3 | Bidding | bid update did not check whether the submitted bid course is the same as previous bidded course | Low | 1 | 1 | Debugged once the bug is spotted
36 | 3 | removebystuandsection | should be removed from "sectionstu"table but not "bid" table | Low | 1 | 1 | Debugged once the bug is spotted
37 | 3 | meet Criteria | misspelling | Low | 1 | 1 | Debugged once the bug is spotted
38 | 4 | Json Drop section | Incorrect error message in Json dropsection | Low | 1 | 1 | Debugged once the bug is spotted
39 | 4 | JSON Dump | JSON output for Dump did not show the correct format for exam start, end and date | High | 5 | 5 | Stopped Current Development and inform the PM. Scheduled another session for debugging.
40 | 4 | JSON Authenticate | JSON output for authenticate is incorrect as we used 'messages' instead of 'message' | Low | 1 | 1 | Debugged once the bug is spotted
41 | 4 | JSON Bid-dump | JSON output incorrect for amount as it returns string, not float | Low | 1 | 1 | Debugged once the bug is spotted
42 | 4 | JSON Dump | JSON output incorrect for amount as it returns string, not float | Low | 1 | 1 | Debugged once the bug is spotted
43 | 4 | JSON section-dump | JSON output incorrect for amount as it returns string, not float | Low | 1 | 1 | Debugged once the bug is spotted
44 | 4 | JSON update-bid | JSON output incorrect for amount as it returns string, not float | Low | 1 | 1 | Debugged once the bug is spotted
45 | 4 | JSON user-dump | JSON output incorrect for amount as it returns string, not float | Low | 1 | 1 | Debugged once the bug is spotted
46 | 4 | JSON Dump | JSON output did not show Day as days, but instead as numbers | Low | 1 | 1 | Debugged once the bug is spotted
47 | 4 | View Bidding results | For a section vacancy of 2 in IS003 S1, 2 students first bid $10. Then, a third person bids $11 but the original 2 were not kicked out of the section | High | 5 | 5 | Stopped Current Development and inform the PM. Scheduled another session for debugging.
48 | 4 | Bootstrap | wrong naming of errors | Low | 1 | 1 | Debugged once the bug is spotted
49 | 4 | User-Dump | wrong output for amount | Low | 1 | 1 | Debugged once the bug is spotted
50 | 4 | common.php | wrong validation for student edollar for bootstrap | Low | 1 | 1 | Debugged once the bug is spotted
51 | 4 | bid-dump.php | JSON output includes round 1 successful bids | Low | 1 | 1 | Debugged once the bug is spotted
52 | 5 | bid-status.php | Vacancy for round 2 inactive is deducted twice | Low | 1 | 1 | Debugged once the bug is spotted
53 | 5 | section-dump.php | Json shows Null when no students in section instead of empty array | Low | 1 | 1 | Debugged once the bug is spotted
54 | 5 | Bootstrap | Student edollar is invalid when it is 1d.p. | High | 5 | 5 | Stopped Current Development and inform the PM. Scheduled another session for debugging.
55 | 5 | Bootstrap | S01 in section number is accepted when it shouldn’t be | High | 5 | 5 | Stopped Current Development and inform the PM. Scheduled another session for debugging.
56 | 5 | Update-bid.php | blank fields not properly validated, as 0 validates as blank | Low | 1 | 1 | Debugged once the bug is spotted
57 | 5 | section-dump.php | Wrong SQL statement ordering | Low | 1 | 1 | Debugged once the bug is spotted
58 | 5 | Drop-section.php | blank fields not properly validated, as 0 validates as blank | Low | 1 | 1 | Debugged once the bug is spotted
59 | 5 | Delete-bid.php | blank fields not properly validated, as 0 validates as blank | Low | 1 | 1 | Debugged once the bug is spotted
60 | 5 | bid-dump.php | wrong error message, empty changed to blank | Low | 1 | 1 | Debugged once the bug is spotted
61 | 5 | authenticate.php | wrong error message | Low | 1 | 1 | Debugged once the bug is spotted
62 | 5 | fail_bidDAO.php | wrong sql statement | Low | 1 | 1 | Debugged once the bug is spotted
63 | 5 | bid-status.php | vacancy was calculated wrongly in round 2 active | Low | 1 | 1 | Debugged once the bug is spotted
64 | 5 | bid-status.php | min_bid was retrieved from studentsection table instead of bid table in round 2 - inactive | Low | 1 | 1 | Debugged once the bug is spotted
65 | 5 | bid-status.php | min_bid could not display correctly in round 2 active | Low | 1 | 1 | Debugged once the bug is spotted
66 | 5 | authenticate.php | error message not out put correctly ie(invalid username\/password instead of invalid username, invalid password) | Low | 1 | 1 | Debugged once the bug is spotted
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
195
196
197
198

## Our Bug Log1
Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team)
1 | 1 | Bootstrap | Not all data was called in the select statement which made it impossible to create course objects. Results were also not appended in an array. retrieve($course) in course DAO | Resolved | 21/9/2019 | 21/9/2019 | YB & SH
2 | 1 | Bootstrap | Not all data was called in the select statement which made it impossible to create prereq object. Results were also not appended in an array. retrieve($course) in Prerequisite DAO | Resolved | 21/9/2019 | 21/9/2019 | YB & SH
3 | 1 | Bootstrap | Spelling error in function name. retrieve($course) in Prerequisite DAO | Resolved | 21/9/2019 | 21/9/2019 | YB & SH
4 | 1 | Bootstrap | Did not Initialise $course_processed | Resolved | 23/9/2019 | 24/9/2019 | YB & SH
5 | 1 | Bootstrap | Returned an array of objects instead of 1 object. retrieve($userid) in StudentDAO | Resolved | 24/9/2019 | 24/9/2019 | SA & LW
6 | 1 | Bootstrap | When appending object in retrieve($course), wrong class (course) was used. retrieve($course) in Prerequisite DAO | Resolved | 24/9/2019 | 24/9/2019 | SA & LW
7 | 1 | Bootstrap | SQL statement only retrieves userid and amount. retrieve($userid) in BidDAO | Resolved | 26/9/2019 | 26/9/2019 | YB & SH
8 | 1 | Bootstrap | Remove function in BidDAP only pass in userid instead of both userid and code | Resolved | 26/9/2019 | 26/9/2019 | YB & SH
9 | 1 | Bootstrap | Empty function treats 0 as empty. Changed to comparison with "" in Common.php | Resolved | 26/9/2019 | 26/9/2019 | YB & SH
10 | 1 | Bootstrap | Updated isEmpty($var) to check if the data is "" and not empty() | Resolved | 23/9/2019 | 24/9/2019 | YB & SH
11 | 1 | Bootstrap | Changed sql statement for retrieveAll(), Changed retrieve(userID) function to return an array, Debugged Remove($userid) function | Resolved | 2019-09-25 | 2019-09-26 | YB & SH
12 | 1 | Bootstrap | Wrong SQL statement changed to * | Resolved | 2019-09-25 | 2019-09-26 | YB & SH
13 | 1 | Bootstrap | Code Sequence wrong, empty() takes 0 as empty, thus changed to string comparison * | Resolved | 2019-09-25 | 2019-09-26 | YB & SH
14 | 2 | Add Bid | Variable names in course class differs from bidhome.php | Resolved | 2019-10-01 | 2019-10-01 | YB & SA
15 | 2 | validate no class time clashed | loops for validating no class time clashed and loops for validating no exam time clashed should not be nested | Resolved | 2019-10-05 | 2019-10-06 | YB & SA
16 | 2 | assign the value to username | hard code username | Resolved | 2019-10-07 | 2019-10-07 | YB & SA
17 | 2 | assign the value to round | hard code round | Resolved | 2019-10-07 | 2019-10-07 | YB & SA
18 | 2 | Round 2 Clearing | Changed variable name | Resolved | 2019-10-10 | 2019-10-10 | JT & SH
19 | 2 | Round 2 Clearing | added min_bid row | Resolved | 2019-10-10 | 2019-10-10 | JT & SH
20 | 2 | Round 2 Clearing | admin_homepage.php doesn’t lead to correct pages when the various buttons are pressed | Resolved | 2019-10-11 | 2019-10-11 | JT & SH
21 | 2 | Round 2 Clearing | bootstrap_process.php had a missing ?> in the php file | Resolved | 2019-10-11 | 2019-10-11 | JT & SH
22 | 2 | Add Bid | Edollar is not updated on bidding.php after submit button. Only edollar left is updated. | Resolved | 2019-10-08 | 2019-10-08 | YB & SA
23 | 2 | Add Bid | bidding.php shows error as did not code what to display if there are no sections available. | Resolved | 2019-10-08 | 2019-10-08 | YB & SA
24 | 2 | Round 2 Clearing | bid table not cleared during clearing | Resolved | 2019-10-11 | 2019-10-12 | JT & SH
25 | 2 | meet Criteria | fail to test the completed course in "course_comp.php" | Resolved | 2019-10-12 | 2019-10-12 | YB & SA
26 | 2 | Bidding | Bidding page cannot access because path called is wrong | Resolved | 2019-10-14 | 2019-10-14 | JT & SA
27 | 2 | Admin Clearing | Failed bids are not added to Fail bid table | Resolved | 2019-10-14 | 2019-10-14 | JT & SA
28 | 3 | JSON Start | Start round message prints 0 when round is 2 | Resolved | 2019-10-15 | 2019-10-15 | JT & SA
29 | 3 | JSON Stop | Did not update student's bid | Resolved | 2019-10-15 | 2019-10-15 | JT & SA
30 | 3 | JSON Start | Did not properly print out message with [] | Resolved | 2019-10-15 | 2019-10-15 | JT & SA
31 | 3 | Round 1 Clearing | added student object instead of bid object into fail_bid table | Resolved | 2019-10-15 | 2019-10-15 | JT & SA
32 | 3 | bidding status | spelling error | Resolved | 2019-10-15 | 2019-10-15 | YB & LW
33 | 3 | bidding status | return wrong message as round is hardcoded | Resolved | 2019-10-15 | 2019-10-15 | YB & LW
34 | 3 | Stop round | updates the round table with wrong status | Resolved | 2019-10-15 | 2019-10-15 | JT & SA
35 | 3 | Bidding | bid update did not check whether the submitted bid course is the same as previous bidded course | Resolved | 15/10/2019 | 15/10/2019 | JT & SA
36 | 3 | removebystuandsection | should be removed from "sectionstu"table but not "bid" table | Resolved | 2019-10-18 | 2019-10-18 | YB & LW
37 | 3 | meet Criteria | misspelling | Resolved | 2019-10-21 | 2019-10-21 | YB & LW
38 | 4 | Json Drop section | Incorrect error message in Json dropsection | Resolved | 2019-10-29 | 2019-10-29 | SH & LW
39 | 4 | JSON Dump | JSON output for Dump did not show the correct format for exam start, end and date | Resolved | 2019-10-30 | 2019-10-30 | JT & YB
40 | 4 | JSON Authenticate | JSON output for authenticate is incorrect as we used 'messages' instead of 'message' | Resolved | 2019-10-31 | 2019-10-31 | JT & YB
41 | 4 | JSON Bid-dump | JSON output incorrect for amount as it returns string, not float | Resolved | 2019-10-31 | 2019-10-31 | JT & YB
42 | 4 | JSON Dump | JSON output incorrect for amount as it returns string, not float | Resolved | 2019-10-31 | 2019-10-31 | JT & YB
43 | 4 | JSON section-dump | JSON output incorrect for amount as it returns string, not float | Resolved | 2019-10-31 | 2019-10-31 | JT & YB
44 | 4 | JSON update-bid | JSON output incorrect for amount as it returns string, not float | Resolved | 2019-10-31 | 2019-10-31 | JT & YB
45 | 4 | JSON user-dump | JSON output incorrect for amount as it returns string, not float | Resolved | 2019-10-31 | 2019-10-31 | JT & YB
46 | 4 | JSON Dump | JSON output did not show Day as days, but instead as numbers | Resolved | 2019-10-31 | 2019-10-31 | JT & YB
47 | 4 | View Bidding results | For a section vacancy of 2 in IS003 S1, 2 students first bid $10. Then, a third person bids $11 but the original 2 were not kicked out of the section | Resolved | 2019-11-05 | 2019-11-06 | SH & LW
48 | 4 | Bootstrap | wrong naming of errors | Resolved | 2019-11-06 | 2019-11-06 | JT & YB
49 | 4 | common.php | wrong validation of student edollar for bootstrap | Resolved | 2019-11-06 | 2019-11-06 | JT & YB
50 | 4 | common.php | wrong validation for student edollar for bootstrap | Resolved | 2019-11-06 | 2019-11-06 | JT & YB
51 | 4 | bid-dump.php | JSON output includes round 1 successful bids | Resolved | 2019-11-12 | 2019-11-12 | SA & SH
52 | 5 | bid-status.php | Vacancy for round 2 inactive is deducted twice | Resolved | 2019-11-12 | 2019-11-12 | SA & SH
53 | 5 | section-dump.php | Json shows Null when no students in section instead of empty array | Resolved | 2019-11-12 | 2019-11-12 | SA & SH
54 | 5 | Bootstrap | Student edollar is invalid when it is 1d.p. | Resolved | 2019-11-12 | 2019-11-13 | SA & SH
55 | 5 | Bootstrap | S01 in section number is accepted when it shouldn’t be | Resolved | 2019-11-16 | 2019-11-16 | SA & SH
56 | 5 | Update-bid.php | blank fields not properly validated, as 0 validates as blank | Resolved | 2019-11-17 | 2019-11-17 | JT & LW
57 | 5 | section-dump.php | Wrong SQL statement ordering | Resolved | 2019-11-17 | 2019-11-17 | JT & LW
58 | 5 | Drop-section.php | blank fields not properly validated, as 0 validates as blank | Resolved | 2019-11-17 | 2019-11-17 | JT & LW
59 | 5 | Delete-bid.php | blank fields not properly validated, as 0 validates as blank | Resolved | 2019-11-17 | 2019-11-17 | JT & LW
60 | 5 | bid-dump.php | wrong error message, empty changed to blank | Resolved | 2019-11-17 | 2019-11-17 | JT & LW
61 | 5 | authenticate.php | wrong error message | Resolved | 2019-11-17 | 2019-11-17 | JT & LW
62 | 5 | fail_bidDAO.php | wrong sql statement | Resolved | 2019-11-17 | 2019-11-17 | JT & LW
63 | 5 | bid-status.php | vacancy was calculated wrongly in round 2 active | Resolved | 2019-11-17 | 2019-11-17 | SA & SH
64 | 5 | bid-status.php | min_bid was retrieved from studentsection table instead of bid table in round 2 - inactive | Resolved | 2019-11-17 | 2019-11-17 | SA & SH
65 | 5 | bid-status.php | min_bid could not display correctly in round 2 active | Resolved | 2019-11-17 | 2019-11-17 | SA & SH
66 | 6 | bid-status.php | error message not out put correctly ie(invalid username\/password instead of invalid username, invalid password) | Resolved | 2019-11-17 | 2019-11-17 | SA & SH

## Bug Metrics SAMPLE
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 2 | Login (User) | Failed login with correct username and correct password | High | 5 | 27 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
2 | 2 | Login (User) | Failed login with correct username and wrong password | High | 5
3 | 2 | Login (User) | Failed login with wrong username and correct password | High | 5
4 | 2 | Login (Admin) | After successful login, login did not store name in session for display use at index_admin | Low | 1
5 | 2 | Login (User) | After successful login, login did not store name in session for display use at index | Low | 1
6 | 2 | Bootstrap | Crashes on upload with a "duplicate entry" database error | Critical | 10
7 | 3 | Bootstrap | Failed to print correct error message for invalid username | Low | 1 | 20 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
8 | 3 | Bootstrap | Failed to validate the "timestamp" in location.csv | Low | 1
9 | 3 | Bootstrap | Printed wrong error messages | Low | 1
10 | 3 | HeatMap | Unable to retrieve Arraylist sucessfully | High | 5
11 | 3 | HeatMap | Fail to load timepicker function | Low | 1
12 | 3 | HeatMap | Cannot load date and time picker function after importing navbar.jsp | Low | 1
13 | 3 | HeatMap | Did not retrieve the last location update | Critical | 10
14 | 4 | Popular Place | Could not print K number of places | High | 5 | 20 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
15 | 4 | Popular Place | Null pointer exception raised when dealing with no data | High | 5
16 | 4 | Popular Place | Could not select "K" | High | 5
17 | 4 | Bootstrap | Could not delete from table when bootstrapping | High | 5
18 | 4 | Breakdown of Y&G | Retreive output table is not aligned properly | Low | 1 | 12 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
19 | 4 | Breakdown of Y&G | Null pointer exception raised when retreiving error message | High | 5
20 | 4 | Breakdown of Y&G | Unable to calculate percentage | Low | 1
21 | 4 | Breakdown of Y&G | Issue when retrieving total number of users, and cause null pointer exceptions | High | 5
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198