## Week 4 (hidden)
Person | Question | Week 4: 14/9/2019 to 15/9/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Jaslyn Toh | What did you do yesterday? | [5 empty] | NIL | Planned for 16/9 meeting
| What will you do today? | [5 empty] | Continue planning for tomorrow's meeting | Make schedule changes and updates
| Do you have any obstacles? | [5 empty] | NIL | NIL
Lai See Hoe | What did you do yesterday? | [5 empty] | NIL | Read up on class and classDAOs and functionalities
| What will you work on today? | [5 empty] | Read up on class and classDAOs | Re-look bootstrap in Pokemon example
| Do you have any obstacles? | [5 empty] | NIL | NIL
Leonard Wong | What did you do yesterday? | [5 empty] | NIL | Re-look at functionalities
| What will you work on today? | [5 empty] | Re-look at Pokemon example given in class | Start planning the code for Bid bootstrap (class, reading & processing of csv)
| Do you have any obstacles? | [5 empty] | NIL | NIL
Serene | What did you do yesterday? | [5 empty] | NIL | Read up on functionalities, classes
| What will you work on today? | [5 empty] | Read up on classes | Revise on classesDAO
| Do you have any obstacles? | [5 empty] | NIL | NIL
Yi Bing | What did you do yesterday? | [5 empty] | NIL | Read up on functionalities, classes
| What will you work on today? | [5 empty] | Revise bootstrap | Plan codes for course and prerequisite class and classDAOS
| Do you have any obstacles? | [5 empty] | NIL | NIL

## Week 5 (hidden)
Person | Question | Week: 16/9 to 23/9
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Jaslyn Toh | What did you do yesterday? | Planned for today's meeting | Relook at functionalities | Coach using the prerequisite csv. | Transfer the schedule into the google sheets | Check for bugs in codes | Prepare test plans for the meeting | Project schedulling to finalise the tasks with respect to the changes made in wiki
| What will you do today? | Relook at functionalities | Coaching using the prerequisite csv. | Transfer the schedule into the google sheets | Check for bugs in codes |  | Project schedulling to finalise the tasks with respect to the changes made in wiki | Not a working day
| Do you have any obstacles? | NIL | NIL | Transferring the schedule is tedious as the formats will be shuffled | NIL |  | Aligning our schedule with the new updates | Not a working day
Lai See Hoe | What did you do yesterday? | Re-look bootstrap in Pokemon example | Plan the functionalities of the DAO and boot strap in section | Create database, Pre requsite class, Prereq class dao and boot strap | Pushed Course, courseDAO, section and sectionDAO | Check for bugs in codes | Discuss test cases and test plans | to complete Section and Course bootstrap
| What will you work on today? | Plan the functionalities of the DAO and boot strap in section | Create database, Pre requsite class, Prereq class dao and boot strap | To push Course, courseDAO, section and sectionDAO | Check for bugs in codes | Discuss test cases and test plans | to complete Section and Course bootstrap | Not a working day
| Do you have any obstacles? | NIL | NIL | Faced slight issues when creating the Prerequisite bootstrap | NIL | NIL | Faced bugs in course DAO | Not a working day
Leonard Wong | What did you do yesterday? | Start planning the code for Bid bootstrap (class, reading & processing of csv) | Start on Bid DAO and Bid.php structure | Continue with bid DAO and Bid.php | Pushed course_completed, course_completedDAO, student, studentDAO, bidDAO and Bid.php | check bugs | Discuss test cases and test plans | Bootstrap creation for student, course_completed and bid and plan validations for bid.csv
| What will you work on today? | Start on Bid DAO and Bid.php structure | Continue with bid DAO and Bid.php | Finishing student, studentDAO, bidDAO and Bid.php | Check for bugs in codes | Discuss test cases and test plans | Bootstrap creation for student, course_completed and bid and plan validations for bid.csv | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | Having slight issue on validation that loop through valid course and invalid section
Serene | What did you do yesterday? | Revise on classesDAO | Read up on pokemon example | Start on student.php and studentDAO.php structure | Aid leonard in pushing codes | Check for bugs in codes | Discuss test cases and test plans | Bootstrap creation for student, course_completed and bid
| What will you work on today? | Read up on Pokemon example | Start on student.php and studentDAO.php structure | Aid leonard in pushing bid, bidDAO, student and studentDAO | Check for bugs in codes | Discuss test cases and test plans | Bootstrap creation for student, course_completed and bid | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | Faced bugs in student DAO | Not a working day
Yi Bing | What did you do yesterday? | Plan codes for course and prerequisite class and classDAOS | Read up on Pokemon example | Create database, Pre requsite class, Prereq class dao and boot strap | Aid See Hoe in pushing course, courseDAO, section and sectionDAO | Check for bugs in codes | Discuss test cases and test plans | Bootstraps creation for Course, Section
| What will you work on today? | Read up on Pokemon example | Create database, Pre requsite class, Prereq class dao and boot strap | Aid See Hoe in pushing course, courseDAO, section and sectionDAO | Check for bugs in codes | group meeting for test case and test plans | Bootstraps creation for Course, Section | Not a working day
| Do you have any obstacles? | NIL | NIL | Faced some issues with PrereqDAO | NIL | NIL | Faced bugs in course DAO | Not a working day

## Week 6 (hidden)
github | Question | Week: <23/9> to <27/9>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Jaslyn Toh | What did you do yesterday? | Not a working day | Plan for schedule | Check test cases, validations, and Debug | Plan for schedule | Testing and debugging with group, carried out meeting | Continue with critical path | Create slides for PM review
| What will you do today? | Plan for the schedule | Check test cases and validations for bootstrap | Plan for schedule | Testing and debugging with the group, plan for meeting (critical path and group progress) | Continue with critical path | Create slides for PM review | Not a working day
| Do you have any obstacles? | NIL | NIL | Faced issues with codes when Debugging | NIL | Faced many bugs yesterday, but were resolved | NIL | NIL
Lai See Hoe | What did you do yesterday? | Not a working day | Test Cases for additional Validation | Validations for bootstrap | Login page and authentication | Testing and debugging with the group | Critical path | Continue with critical path
| What will you work on today? | Test Cases for additional Validation | Validations for bootstrap | Login page and authentication | Testing and debugging with the group | Critical path | Continue with critical path | Not a working day
| Do you have any obstacles? | NIL | NIL | Faced issues with codes when Debugging yesterday | faced issues when using css | NIL | NIL | NIL
Leonard Wong | What did you do yesterday? | Not a working day | Test Cases for additional Validation | Validations for bootstrap | Not a working day | Testing and debugging with the group | Critical path | Continue with critical path
| What will you work on today? | Test Cases for additional Validation | Validations for bootstrap | Not a working day | Testing and debugging with the group | Critical path | Continue with critical path | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | Faced bugs with bid | NIL | NIL
Serene | What did you do yesterday? | Not a working day | Test cases for validations | Validations for bootstrap | Not a working day | Testing and debugging | Critical path | Continue with critical path
| What will you work on today? | Test cases for validations | Validations for bootstrap | Not a working day | Testing and debugging | Critical path | Continue with critical path | Not a working day
| Do you have any obstacles? | NIL | NIL | Not a working day | NIL | Had a slight github issue yesterday as I forgot to pull from repo before commiting, but was resolved | NIL | NIL
Yi Bing | What did you do yesterday? | Not a working day | Test cases for validations | Validations for bootstrap | Login page and authentication | Testing and debugging | Critical path | Continue with critical path
| What will you work on today? | Test case for validations | Validations for bootstrap | Login page and authentication | Testing and debugging | Critical path | Continue with critical path | Not a working day
| Do you have any obstacles? | NIL | NIL | Faced issues with codes when Debugging yesterday | Faced issues with css | NIL | NIL | NIL

## Week 7 (hidden)
github | Question | Week: <28/9> to <4/10>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Jaslyn Toh | What did you do yesterday? | Not a working day | Create and pushed Admin Landing page | Start on Round 1 starting logic | Push round 1 starting logic, start on round 1 clearing logic | Finalise and push round 1 clearing for admin | Create test cases for round 1 starting logic & clearing logic | Not a working day
| What will you do today? | Create Admin Landing page | Start on Round 1 starting logic | Push round 1 starting logic, start on round 1 clearing for admin | Finalise and push round 1 clearing for admin | Create test cases for round 1 starting logic & clearing logic | Not a working day | Round 2 admin 'start'
| Do you have any obstacles? | NIL | NIL | NIL | Faced difficulties when planning for the steps to update students on their status -> resolved | NIL | NIL | Still trying to figure out round 2 clearing logic
Lai See Hoe | What did you do yesterday? | Not a working day | Create Admin Landing page | Start on Round 1 starting logic | Push round 1 starting logic, start on round 1 clearing logic | Finalise and push round 1 clearing for admin | Create test cases for round 1 starting logic & clearing logic | Not a working day
| What will you work on today? | Create Admin Landing page | Start on Round 1 starting logic | Push round 1 starting logic, start on round 1 clearing for admin | Finalise and push round 1 clearing for admin | Create test cases for round 1 starting logic & clearing logic | Not a working day | starting round 2
| Do you have any obstacles? | NIL | NIL | NIL | Faced difficulties when planning for the steps to update students on their status -> resolved | NIL | NIL | NIL
Leonard Wong | What did you do yesterday? | Not a working day | Plan for next meeting | Check Admin Landing page | Check round 1 starting logic | Check Round 1 bidding logic | Test all the logic again & update schedule | Not a working day
| What will you work on today? | Plan for next meeting | Check Admin Landing page | Check round 1 starting logic | Check Round 1 bidding logic | Test all the logic again & update schedule | Not a working day | CSS on admin home page + bidding apge
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Serene | What did you do yesterday? | Not a working day | Create Bid page UI | Start Round 1 Bidding Logic | Continue Round 1 Bidding | Testing & debugging of Round 1 bidding | Create test cases for Round 1 bidding | Not a working day
| What will you work on today? | Create Bid page UI | Start Round 1 Bidding Logic | Continue Round 1 Bidding | Testing & debugging of Round 1 bidding | Create test cases for Round 1 bidding | Not a working day | Round 2 bidding logic
| Do you have any obstacles? | NIL | Converting pseudocode to code | NIL | NIL | NIL | NIL | NIL
Yi Bing | What did you do yesterday? | Not a working day | Create Bid page UI | Start Round 1 Bidding Logic | Continue Round 1 Bidding | Testing & debugging of Round 1 bidding | Create test cases for Round 1 bidding | Not a working day
| What will you work on today? | Create Bid page UI | Start Round 1 Bidding Logic | Continue Round 1 Bidding | Testing & debugging of Round 1 bidding | Create test cases for Round 1 bidding | Not a working day | Round 2 bidding logic
| Do you have any obstacles? | NIL | Converting pseudocode to code | NIL | NIL | NIL | NIL | NIL

## Week 8
github | Question | Week: <5/10> to <11/10>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Jaslyn Toh | What did you do yesterday? | Plan for Round 2 admin 'start' | Round 2 start
| What will you do today? | continue with round 2 and start clearing round 2 | Continue with round 2 start
| Do you have any obstacles? | NIL | NIL
Lai See Hoe | What did you do yesterday? | starting round 2 | continue with round 2 and start clearing round 2
| What will you work on today? | continue with round 2 and start clearing round 2 | Continue with round 2 start
| Do you have any obstacles? | NIL | NIL
Leonard Wong | What did you do yesterday? | CSS on admin home page + bidding apge | help in round 2
| What will you work on today? | help in round 2 | Plan for JSON logic for web service
| Do you have any obstacles? | NIL | NIL
Serene | What did you do yesterday? | Round 2 bidding logic | continue round 2 bidding logic
| What will you work on today? | continue round 2 bidding logic | continue round 2 bidding logic
| Do you have any obstacles? | NIL | NIL
Yi Bing | What did you do yesterday? | Round 2 bidding logic | continue round 2 bidding logic
| What will you work on today? | continue round 2 bidding logic | continue round 2 bidding logic
| Do you have any obstacles? | NIL | NIL

## Week 9
github | Question | Week: <12/10> to <18/10>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Jaslyn Toh | What did you do yesterday?
What will you do today?
Do you have any obstacles?
Lai See Hoe | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Leonard Wong | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Serene | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Yi Bing | What did you do yesterday?
What will you work on today?
Do you have any obstacles?